►Findings shared with Droplet re: alert system limitations in busy Ward environment                                 ►IPC Nurse attending staff meetings to emphasis importance of hydration and accurate recording          ►Further project commenced to address urine dip analysis in line with Public Health England                   ►Older Adult training scheduled re: nutrition, hydration & mealtime experience for people living with dementia                                                                                                                                                        ►#LoveHydration Project Team planning events throughout the summer

All teach, all learn

►Review of fluid charts – inconsistencies identified                         ►Review of urinary tract infections and prescriptions for antibiotics -   further projects identified to address urine analysis issues                           ►Use of Droplet products monitored   ►Staff and patient feedback collected

Study

►Project launched Feb 14 to promote #LoveHydration with gift/info bags for staff                                        ►Droplet products with visual/vocal alert system introduced on Langworth Ward                                                           ►Droplet mugs/beakers and strong flavoured squash introduced at Manthorpe Centre               ► Risk Assessment created for products

Do

►Droplet mugs/beakers continue to be used with positive feedback                                  ►Droplet bases unsuitable for Ward environment; shared with Community Teams                                                 ►Wards supplied with variety of drinks to continue hydration promotion & meet patient preferences

Act

Gift & Information bags for staff

QUALITY

IMPROVEMENT

Older Adult Inpatient Division

#Love Hydration Innovation project 2018/2019

Change idea: To improve patient hydration levels by introducing ‘Droplet’ Products

►Evidence of increased incidence of urinary tract infections during summer months on Wards                ►Research indicates hydration levels directly linked to issues such as falls and increased confusion in older adults                                       ►’Droplet’ product, designed for older adults, has evidenced improved levels of hydration

Why is this important?

►Invite ‘Droplet’ to demo product                            ►Submit idea for LPFT Innovation Funding   ►Identify 2 pilot sites, one to use ‘Droplet’, 1 to be control                                                              ►Set launch date                                                      ►Collect baseline data 4 weeks prior to start   ►Engage Ward Staff, Patients/Carers

Plan